## Sheet1
High-Level Task | Resource(s)
Manage | Project Sponsor
Plan Project | Business Project Manager
Concept Exploration | Enterprise Architect, Solution Architect
Organize Project | Business Project Manager
Infrastructure Build | Information Technology Manager, Production Supervisor
Baseline Servers | System Administrator, Network Administrator, Security Manager, Database Administrator
Informatica Software Install | System Administrator, Network Administrator, Security Manager, Informatica Administrator
Development Environment Set-up | System Administrator, Network Administrator, Security Manager, Informatica Administrator
Analyze | Technical Project Manager, Process Owner
High-Level Requirements Gathering | Solution Architect, Data Analyst, Data Architect, Data Steward/ DQ Steward, Process Owner
Preliminary Data Assessment | Data Analyst, Data Architect, Data Steward/ DQ Steward
Preliminary Solution Architecture | Enterprise Architect, Solution Architect
Gap Analysis | Solution Architect
Detailed Requirements Specifications | Solution Architect
Final Data Assessment | Solution Architect, Data Analyst, Data Architect, Data Steward/ DQ Steward
Architect | Technical Project Manager
Finalize Solution Architecture | Solution Architect
Finalize Operating Environment Specifications | Solution Architect
Design | Technical Project Manager
Design Physical Data Model | Solution Architect
Design Technical Solution | Solution Architect
Design Business Rules | Solution Architect
Design Policies and Procedures | Solution Architect
Update RTM with design specification references | Solution Architect
Build | Technical Project Manager
Build the Informatica MDM Hub | Application Specialist
UI config/changes/customizations - for Data Stewardship | Application Specialist
Build Hierarchies | Application Specialist
Build Workflows | Application Specialist
Build custom solutions | Application Specialist
Build Reports | Application Specialist
Tune the rules | Application Specialist
Round 1: Load small data set for all sources | Application Specialist, Data Quality Developer, Data Integration Developer
Round 2: Load representative data set for all sources | Application Specialist, Data Quality Developer, Data Integration Developer
Round 3: Load representative data set for all sources | Application Specialist, Data Quality Developer, Data Integration Developer
Update Business Rules document with any rule changes | Application Specialist
Loading the Hub (data)
Build job control processes | Application Specialist
Build initial load processes | Application Specialist, Data Quality Developer, Data Integration Developer
Build the interfaces | Application Specialist, Data Quality Developer, Data Integration Developer
Test | Technical Project Manager
Test Planning and Preparation | Quality Assurance Manager
MDM Data Refresh & Load (Reference Data Refresh) | Data Integration Developer
System Testing | Test Engineer, Informatica Administrator
Volume and Performance Testing | Test Engineer, Data Integration Developer
User Acceptance Testing (UAT) | User Acceptance Test Lead, Data Steward/DQ Steward
Finalize Testing Report | Test Engineer
Testing Phase Checkpoints | Test Engineer
Deploy | Technical Project Manager, Information Technology Manager
Production Environment Set-up | Production Supervisor, System Administrator, Network Administrator, Security Manager, Informatica Administrator, Database Administrator
Prepare to deploy | Process Owner, Production Supervisor, System Administrator, Network Administrator, Security Manager, Informatica Administrator, Database Administrator
Check Points | System Administrator, Network Administrator, Security Manager
Deliver KT to Customer | Application Specialist
Rollout | Production Supervisor, System Administrator, Network Administrator, Security Manager, Informatica Administrator, Database Administrator