## Analytics Modernization Plan
High-Level Task | Resource(s)
Manage | Project Sponsor
Conduct Kickoff call with Stakeholders | Project Sponsor, Technical Project Manager
Plan Project | Business Project Manager, Technical Project Manager
Concept Exploration | Enterprise Information Architect, Solution Architect, Data Architect
Infrastructure Build | Information Technology Manager, Production Supervisor
Baseline Servers | Network Administrator, Security Manager, Database Administrator
Development Environment Set-up | Network Administrator, Security Manager, Informatica Administrator
Create Project Charter and share with share holders | Business Project Manager, Technical Project Manager
Create and maintain the Issue and Risk log for tracking | Business Project Manager, Technical Project Manager
Analyze
Conduct workshops for requirement gathering | Business Analyst, Solution Architect, Data Integration Architect, Data Steward/Data Quality Steward, Metadata Manager
Formulate the business use case | Business Analyst, Solution Architect, Data Integration Architect, Data Steward/Data Quality Steward, Metadata Manager
Create Business Requirement Document | Business Analyst, Solution Architect, Data Integration Architect, Data Steward/Data Quality Steward, Metadata Manager
Get the Requirements reviewed by Stakeholders | Business Analyst, Solution Architect, Data Integration Architect, Data Steward/Data Quality Steward, Metadata Manager
Get sign off for Requirements from User Acceptance Test Lead | Business Analyst, Solution Architect, User Acceptance Test Lead
Architect and Design
Design the overall Solution Architecture | Solution Architect, Data Integration Architect , Enterprise Architect
Design the Data model for Cloud Data lake and Cloud Datawarehouse | Data Architect, Data Stewards, Data Integration Architect, Solution Architect, Enterprise Architect
Design the Deployment architecture of secure agent configuration | Data Architect, Data Integration Architect, Solution Architect
Review the Deployment architecture with Stakeholders and get sign off for Deployment architecture | Data Architect, Data Stewards, User Acceptance Test Lead, Enterprise Architect, Solution Architect
Design RASIC matrix for CDGC | Data Architect, Data Stewards, Solution Architect ,Metadata Manager
Design CDGC Implementation strategies | Data Architect, Solution Architect, Metadata Manager
Create physical objects in Cloud Data Lake and Data Warehouse | Data Architect, Solution Architect, Data Integration Developer
Finalize design for Error handing, Exception handling, Job recovery | Data Integration Architect, Solution Architect
Design for Historical Load/Day 0 data migration if applicable | Data Integration Architect, Solution Architect
Design ETL specification (Source to Target Mapping Specification) | Data Integration Architect, Solution Architect
Obtain sign off for ETL specification | Data Integration Architect, Solution Architect
Analyze dependencies in Jobs | Data Integration Architect, Solution Architect
Design Jobs flows for data extraction, enrichment, data quality and cleansing | Data Integration Architect, Solution Architect
Environment Setup (Non-Production)
Prerequisites Validation
Validate the prerequisites for IICS agent | Data Integration Developer, Data Integration Architect, Network Administrator
Grant IICS agent server access to Data Integration Developers | Application Specialist, Data Integration Architect
Approve read only access to source for Data Integration Developers | Business Project Manager, Informatica Administrator
Grant read only access to source Database’s for Data Integration Developers | Data Base Administrator, Data Integration Architect
Approve Data warehouse access for Data Integration Developers | Data Warehouse Administrator
Grant required privileges to service accounts/consultants as provided in Documentation | Database Administrator, Data Integration Architect
Open firewall to establish connectivity between IICS agent and IDMC endpoint URL | Network Administrator, Data Integration Architect, Informatica Administrator
Installation and configuration
Install IICS secure agent | Informatica Administrator, Data Integration Developer, Data Integration Architect
Configure/Reconfigure the secure agent | Informatica Administrator, Data Integration Developer, Data Integration Architect
Create Users and User-Groups in IICS and assign corresponding privileges based on role | Informatica Administrator, Data Integration Developer
Configure IICS agent group for High availability (If applicable) | Informatica Administrator, Data Integration Developer
Update customized setting to IICS wherever applicable | Informatica Administrator, Data Integration Developer
Design deployment architecture for IICS | Informatica Administrator, Data Integration Developer
Identify required connectors and enable them | Informatica Administrator, Data Integration Developer
Configure required connections in IICS and GDGC | Informatica Administrator, Data Integration Developer
Enable “RunAJob” CLI in IICS ORG | Informatica Administrator, Data Integration Developer
Share the service user credentials for source & Target | Informatica Administrator, Data Integration Developer
Build Catalog
Configure catalog source and metadata extraction | Metadata Manager
Data profiling and domain discovery | Data Integration Developer, Data Integration Architect
Business term association with Technical metadata | Data Integration Developer, Data Integration Architect
Understand source data inter-relationships, volumes, complexity, frequency of change and availability | Data Integration Developer, Data Integration Architect
Develop Analytics Approach
Evaluate and curate use cases using CDGC based on pattern and behavior | Data Integration Developer, Data Integration Architect
Perform gap analysis using CDGC | Data Integration Developer, Data Integration Architect
Decide appropriate modeling technique based on pattern and segmentation | Data Integration Developer, Data Integration Architect
Build and Prepare Data Sets
Gather sample data using CDGC | Data Steward/Data Quality Steward, Data Warehouse/Data Lake Administrator
Build/validate processes to make sure that data from source systems and third parties is available for acquisition | Data Integration Developer, Data Integration Architect
Understand source data inter-relationships, volumes, frequency of change and availability, complexity and filtering requirements | Data Integration Developer, Data Integration Architect, Data Steward/Data Quality Steward
Build pipelines to ingest batch and near real time data using IICS and CDC | Data Integration Developer, Data Integration Architect, Data Steward/Data Quality Steward
Build pipelines to ingest streaming/real time data using IICS | Data Integration Developer, Data Integration Architect, Data Steward/Data Quality Steward
Build necessary data sampling techniques and processing requirements in the pipelines | Data Integration Developer, Data Integration Architect, Data Steward/Data Quality Steward
Perform data cleansing/validation using Data Quality transformations | Data Quality Steward, Data Integration Developer, Data Integration Architect
Build necessary data sampling techniques and processing capabilities in the pipelines | Data Integration Developer, Data Integration Architect, Data Steward/Data Quality Steward
Deploy - Build the Scalable, High-Performance, Production-Ready Systems
Operationalize the pipelines using IICS and CGDC | Data Steward/Data Quality Steward, Data Warehouse/Data Lake Administrator, Informatica Administrator
Optimize/tune the data lake ecosystem to scale and sustain data volumes and pipelines/models complexity from production deployment | Data Steward/Data Quality Steward, Data Warehouse/Data Lake Administrator, Informatica Administrator
Measure and Monitor
Measure effectiveness by correlating business outcomes and actionable insights | Data Integration Developer, Data Integration Architect, Solution Architect
Calibrate the models by continuous discovery, analysis and models' maturity | Informatica Administrator
Monitor the outcomes using appropriate metadata and visualization methods | Business Project Manager, Technical Project Manager
Operationalize the above processes in a cyclical order for continuous maturity and improvements in business outcomes | Business Project Manager, Technical Project Manager
Build analytics report/Visualization layer for business | Application Specialist, Solution Architect
Operate
Transfer knowledge to Operations team | Data Integration Developer, Data Integration Architect, Solution Architect
Schedule the jobs to run in Production and enable the schedule | Informatica Administrator
Create project closure report | Business Project Manager, Technical Project Manager