## Sheet1
High-Level Task | Resource(s)
Manage | Project Sponsor
Plan Project | Business Project Manager
Concept Exploration | Process Architect, Solution Architect, Technical Architect
Organize Project | Business Project Manager
Infrastructure Build | Information Technology Manager, Production Supervisor
Baseline Servers | Network Administrator, Security Manager
Secure Agent Install | Network Administrator, Security Manager, Informatica Administrator
Development Environment Set-up | Network Administrator, Security Manager, Informatica Administrator
Analyze
High-Level Requirements Gathering | Solution Architect, Technical Architect, Data Steward, Business Analysts
Preliminary Solution Architecture | Solution Architect, Technical Architect
Detailed Requirements Specifications including source and target data | Solution Architect, Technical Architect,Data Steward, Business Analysts
Architect
Design the overall Solution Architecture | Solution Architect, Data Integration Architect
Design the Data model for Target system | Data Architect, Data Stewards, Data Integration Architect, Solution Architect
Design load strategies for Cloud Datawarehouse | Data Integration Architect, Solution Architect
Design Data Integration Architecture | Data Integration Architect, Solution Architect
Assess Source data | Data Architect, Solution Architect
Design
Physical object creation in target system | Data Architect, Solution Architect
Design for Historical Load/Day 0 data migration if applicable | Data Integration Architect, Solution Architect
Design ETL specification (Source to Target Mapping Specification) | Data Integration Architect, Solution Architect
Analyse dependencies in Jobs | Data Integration Architect, Solution Architect
Design Jobs flows for data extraction, enrichment and cleansing | Data Integration Architect, Solution Architect
Identify Key Data metrics and dimensions for reporting | Application Specialist, Solution Architect
Environment Setup
Prerequisites Validation
Validate the prerequisites for IICS agent | Data Integration Developer, Data Integration Architect, Network Administrator
Grant IICS agent server access to Data Integration Developers | Application Specialist, Data Integration Architect
Approve read only access to source for Data Integration Developers | Business Project Manager, Informatica Administrator
Grant read only access to source Database’s for Data Integration Developers | Data Base Administrator, Data Integration Architect
Approve target database access for Data Integration Developers | Data Warehouse Administrator
Grant required privileges to service accounts/consultants as provided in Documentation | Database Administrator, Data Integration Architect
Open firewall to establish connectivity between IICS agent and source/target DB's. | Network Administrator, Data Integration Architect, Informatica Administrator
Installation and Configuration
Install IICS secure agent | Informatica Administrator, Data Integration Developer, Data Integration Architect
Configure/Reconfigure the secure agent | Informatica Administrator, Data Integration Developer, Data Integration Architect
Create Users and User-Groups in IICS and assign corresponding privileges based on role. | Informatica Administrator, Data Integration Developer
Configure IICS agent group for High availability (If applicable) | Informatica Administrator, Data Integration Developer
Update customized setting to IICS wherever applicable | Informatica Administrator, Data Integration Developer
Design deployment architecture for IICS | Informatica Administrator, Data Integration Developer
Identify required connectors and enable them | Informatica Administrator, Data Integration Developer
Configure required connections in IICS | Informatica Administrator, Data Integration Developer
Enable “RunAJob” CLI in IICS ORG | Informatica Administrator, Data Integration Developer
Share the service user credentials for source & Target | Informatica Administrator, Data Integration Developer
Create the required connections in IICS level | Informatica Administrator, Data Integration Developer
Build
Build mappings for data processing | Data Integration Developer, Data Integration Architect
Design and build task flows considering data dependencies | Data Integration Developer, Data Integration Architect
Leverage pushdown/Partitioning capability where every applicable | Data Integration Developer, Data Integration Architect
Load the data into target database | Data Integration Developer, Data Integration Architect
Build analytics report/Visualization layer for business | Application Specialist, Solution Architect
Test
Unit test the Data integration Jobs | Data Integration Developer, Data Integration Architect
Perform Integration testing and validate the data | Data Integration Developer, Data Integration Architect
Perform UAT | Business Analyst/Data Stewards
UAT Support | Data Integration Developer, Data Integration Architect
Get Sign off from BU Lead | Technical Project Manager, Solution Architect, User Acceptance Test lead
Deploy
Set up PROD setup and Deployment | Informatica Administrator, Data Integration Developer
Deploy the code in Production | Informatica Administrator, Data Integration Developer, Data Integration Architect
Run Day 0/Initial load | Informatica Administrator, Data Integration Developer, Data Integration Architect
Operate
Knowledge transfer to Operations team | Data Integration Developer, Data Integration Architect, Solution Architect
Schedule the jobs to run in Production and enable schedule | Informatica Administrator
Create project closure report | Business Project Manager, Technical Project Manager