## Data_Lake_Project_Plan
High-Level Task | Resource(s)
Manage | Project Sponsor
Plan Project | Business Project Manager, Technical Project Manager
Concept Exploration | Business Project Manager, Technical Project Manager
Organize Project | Business Project Manager, Technical Project Manager
Infrastructure Build | Information Technology Manager, Production Supervisor, Technical Project Manager
Baseline Servers | Network Administrator, Security Manager, Database Administrator, DW/Data Lake Administrator, Informatica Administrator
Informatica Software Install | Network Administrator, Security Manager, Database Administrator, DW/Data Lake Administrator, Informatica Administrator
Development Environment Set-up | Network Administrator, Security Manager, Database Administrator, DW/Data Lake Administrator, Informatica Administrator
Analyse | Business Project Manager, Technical Project Manager
High-Level Requirement Gathering | Business Analyst, Technical Project Manager, Technical Architect
File Validation Framework – Not Required for Schema Driven Files like Avro, Parquet (Delimited and Fixed Width. Type of Validations: Header Validation, Footer Validation, Record Count, Datatype Checks etc.,) | Business Analyst, Technical Architect
File Load Types (Incremental Load and Full Load) | Business Analyst, Technical Architect
RDBMS Sources Load Types (Incremental Load and Full Load) | Business Analyst, Technical Architect
Partitioning Strategy, Management & Archival | Business Analyst, Technical Architect
Job Parameterization Framework (Not Applicable for DBMI with CDC Configuration) | Technical Architect, Data Integration Developer, Data Transformation Developer
Preliminary Data Assessment | Data Architect, Technical Architect
Data Quality Checks finalization | Technical Architect, Data Scientist, Data Quality Developer, Data Quality Steward
Dynamic Templates for File ingestion - Depending on the Services and Ingestion Patterns (supporting daily and monthly snapshot load types) | Technical Architect, Data Architect, Data Integration Developer
Dynamic Templates for RDBMS table ingestion - Depending on the Services and Ingestion Patterns (supporting daily snapshot, monthly snapshot, daily incremental, monthly incremental, truncate reload, schema drift) | Technical Architect, Data Architect, Data Integration Developer
Preliminary Solution Architecture | Technical Architect, Data Architect
Miscellaneous Reusable Components (Examples: Templates, Patterns, Design Documents etc.,) | Technical Architect, Data Architect, Data Integration Developer
Orchestration and Scheduling | Business Analyst, Technical Architect
Discussion to semi-automate registry of ingestion data sources (Applicable for New Files and Tables as part of Phase 2) | Business Analyst, Technical Architect
Gap Analysis | Technical Architect
Detailed Requirements Specifications | Technical Architect
Final Data Assessment | Technical Architect, Business Analyst, Data Scientist
Architect | Technical Project Manager
Finalize Solution Architecture | Technical Architect
Finalize Operating Environment Specifications | Technical Architect
Design | Technical Project Manager
Design Physical Data Model | Technical Architect
Design Technical Solution | Technical Architect, Data Integration Developer, Data Transformation Developer
Design Business Rules | Technical Architect, Data Quality Steward, Data Quality Developer
Publish Design Document | Technical Architect
Build | Technical Project Manager
Development and Unit Testing of Ingestion Templates (File & RDBMS Sources) | Data Integration Developer, Data Transformation Developer, Quality Assurance Manager
DDL Creation and deployment of Control Tables Data Structures on Development environment (As applicable) | Data Integration Developer, Data Transformation Developer, Quality Assurance Manager, Database Administrator
Development and Unit Testing of File Validation Job (As applicable) | Data Integration Developer, Data Transformation Developer, Quality Assurance Manager
Development and Unit Testing of Reusable Parametrization Job (As applicable) | Data Integration Developer, Data Transformation Developer, Quality Assurance Manager
Development and Unit Testing of other Miscellaneous Reusable Components (As applicable) | Data Integration Developer, Data Transformation Developer, Quality Assurance Manager
Development and Unit Testing of Dynamic Templates for Files (supporting daily and monthly snapshot load types) | Data Integration Developer, Data Transformation Developer, Quality Assurance Manager
Development and Unit Testing of Dynamic Templates for Relational Tables (supporting daily snapshot, monthly snapshot, daily incremental, monthly incremental, truncate reload, schema drift) | Data Integration Developer, Data Transformation Developer, Quality Assurance Manager
DDL creation of data structures/storage structure/buckets on Data Lake Raw Layer (Semi - Automated) | Data Integration Developer, Data Transformation Developer, Quality Assurance Manager, Database Administrator
Support development of poll-based ingestion readiness check for confirming the loading readiness of RDBMS tables. | Data Integration Developer, Data Transformation Developer, Quality Assurance Manager
Development and Unit Testing of Orchestration and Job Scheduling Jobs | Data Integration Developer, Data Transformation Developer, Quality Assurance Manager
Development and Unit testing of Archival Jobs | Data Integration Developer, Data Transformation Developer, Quality Assurance Manager
Publish Operating Manual along with Operations manual consisting of Maintenance guidelines for Informatica Data Lake Mass Ingestion Jobs and steps required to register a new data source. | Data Integration Developer, Data Transformation Developer, Quality Assurance Manager
Test | Technical Project Manager, Business Project Manager
Test Planning and Preparation | User Acceptance Test Lead, Test Engineer, Technical Architect, Quality Assurance Manager
Operationalization of Data Lake Mass Ingestion Jobs (depending on the type of Implementation) | Data Integration Developer
Onboarding and Operationalization of file types and RDBMS tables for Ingestion for Phase 1 Implementation (depending on the type of Implementation) | Metadata Manager, Data Integration Developer
End to End two rounds of execution covering all the developed components | Test Engineer, Data Integration Developer, Quality Assurance Manager
System Testing | Test Engineer, Data Integration Developer, Quality Assurance Manager
Volume and Performance Testing | Test Engineer, Data Integration Developer, Quality Assurance Manager
User Acceptance Testing (UAT) | User Acceptance Test Lead, Test Engineer, Quality Assurance Manager, Data Integration Developer
Finalize Testing Report | User Acceptance Test Lead, Test Engineer, Quality Assurance Manager, Data Integration Developer
Testing Phase Checkpoints | User Acceptance Test Lead, Test Engineer, Technical Architect, Quality Assurance Manager
Publish Test Results document | Test Lead, Test Engineer
Deploy | Technical Project Manager, Information Technology Manager, Business Project Manager
Production Environment Set-up | Production Supervisor, Network Administrator, Security Manager, Informatica Administrator, Database Administrator, DW/Data Lake Administrator
Prepare to Deploy | Production Supervisor, Network Administrator, Security Manager, Informatica Administrator, Database Administrator, DW/Data Lake Administrator, Data Integration Developer
Deployment of Informatica Data Lake Mass Ingestion Jobs to Production Environment (depending on the type of Implementation) | Data Integration Developer, Production Supervisor, Informatica Administrator, Database Administrator, DW/Data Lake Administrator
Operationalization of Informatica Data Lake Mass Ingestion Jobs on production with File types and RDBMS Data Sources for Ingestion for Phase 1 Implementation | Data Integration Developer, Production Supervisor, Informatica Administrator, Database Administrator, DW/Data Lake Administrator, Metadata Manager
Monitoring and Checkpoints | Production Supervisor, Informatica Administrator, DW/Data Lake Administrator, Database Administrator
Continuous Monitoring and Performance tuning of deployed jobs | Production Supervisor, Informatica Administrator, DW/Data Lake Administrator, Database Administrator, Technical Architect, Data Integration Developer
Rollout | Production Supervisor, Informatica Administrator, DW/Data Lake Administrator, Database Administrator, Technical Architect, Data Integration Developer, Data Steward
Deliver KT to Customer | Production Supervisor, Informatica Administrator, DW/Data Lake Administrator, Database Administrator, Technical Architect, Data Integration Developer, Data Steward
Release Production environment for Users | Production Supervisor, Informatica Administrator, DW/Data Lake Administrator, Database Administrator, Technical Architect, Data Integration Developer, Data Steward