## Sheet1
High-Level Task | Resource(s)
Manage | Project Sponsor
Conduct Kickoff call with Stakeholders | Project Sponsor, Technical Project Manager
Plan Project | Business Project Manager, Technical Project Manager
Concept Exploration | Enterprise Information Architect, Solution Architect, Data Architect
Infrastructure Build | Information Technology Manager, Production Supervisor
Baseline Servers | Network Administrator, Security Manager, Database Administrator
Secure Agent Install | Network Administrator, Security Manager, Informatica Administrator
Development Environment Set-up | Network Administrator, Security Manager, Informatica Administrator
Create Project Charter and share with share holders | Business Project Manager, Technical Project Manager
Create and maintain the Issue and Risk log for tracking | Business Project Manager, Technical Project Manager
Analyze
Conduct workshops for requirement gathering | Business Analyst, Solution Architect, Data Integration Architect
Identify Business use cases for Cloud Datawarehouse | Business Analyst, Solution Architect, Data Integration Architect
Create Business Requirement Document | Business Analyst, Solution Architect, Data Integration Architect
Get the Requirements reviewed by Stakeholders | Business Analyst, Solution Architect
Get sign off for Requirements from User Acceptance Test Lead | Business Analyst, Solution Architect, User Acceptance Test Lead
Architect
Design the overall Solution Architecture | Solution Architect, Data Integration Architect
Design the Data model for Target Datawarehouse | Data Architect, Data Stewards, Data Integration Architect, Solution Architect
Review the data model with Stakeholders and get sign off for Data model | Data Architect, Data Stewards, User Acceptance Test Lead
Design load strategies for Cloud Datawarehouse | Data Integration Architect, Solution Architect
Design Data Integration Architecture | Data Integration Architect, Solution Architect
Assess Data which has to be migrated from existing DW to cloud | Data Architect, Solution Architect
Build roadmap for Cloud Datawarehouse | Data Architect, Solution Architect
Design
Create physical objects in Cloud Data Warehouse | Data Architect, Solution Architect
Finalize design for Error handing, Exception handling, Job recovery | Data Integration Architect, Solution Architect
Design for Historical Load/Day 0 data migration if applicable | Data Integration Architect, Solution Architect
Design ETL specification (Source to Target Mapping Specification) | Data Integration Architect, Solution Architect
Obtain sign off for ETL specification | Data Integration Architect, Solution Architect
Analyze dependencies in Jobs | Data Integration Architect, Solution Architect
Design Jobs flows for data extraction, enrichment and cleansing | Data Integration Architect, Solution Architect
Identify Key Data metrics and dimensions for reporting | Application Specialist, Solution Architect
Environment Setup (Non-Production)
Prerequisites Validation
Validate the prerequisites for IICS agent | Data Integration Developer, Data Integration Architect, Network Administrator
Grant IICS agent server access to Data Integration Developers | Application Specialist, Data Integration Architect
Approve read only access to source for Data Integration Developers | Business Project Manager, Informatica Administrator
Grant read only access to source Database’s for Data Integration Developers | Data Base Administrator, Data Integration Architect
Approve Data warehouse access for Data Integration Developers | Data Warehouse Administrator
Grant required privileges to service accounts/consultants as provided in Documentation | Database Administrator, Data Integration Architect
Open firewall to establish connectivity between IICS agent | Network Administrator, Data Integration Architect, Informatica Administrator
Installation and configuration
Install IICS secure agent | Informatica Administrator, Data Integration Developer, Data Integration Architect
Configure/Reconfigure the secure agent | Informatica Administrator, Data Integration Developer, Data Integration Architect
Create Users and User-Groups in IICS and assign corresponding privileges based on role | Informatica Administrator, Data Integration Developer
Configure IICS agent group for High availability (If applicable) | Informatica Administrator, Data Integration Developer
Update customized setting to IICS wherever applicable | Informatica Administrator, Data Integration Developer
Design deployment architecture for IICS | Informatica Administrator, Data Integration Developer
Identify required connectors and enable them | Informatica Administrator, Data Integration Developer
Configure required connections in IICS | Informatica Administrator, Data Integration Developer
Enable “RunAJob” CLI in IICS ORG | Informatica Administrator, Data Integration Developer
Share the service user credentials for source & Target | Informatica Administrator, Data Integration Developer
Build
Build mappings for data processing | Data Integration Developer, Data Integration Architect
Design and build task flows considering data dependencies | Data Integration Developer, Data Integration Architect
Leverage pushdown/Partitioning capability where every applicable | Data Integration Developer, Data Integration Architect
Load the data into Cloud Data Warehouse | Data Integration Developer, Data Integration Architect
Build analytics report/Visualization layer for business | Application Specialist, Solution Architect
Test
Unit test the Data integration Jobs | Data Integration Developer, Data Integration Architect
Perform Integration testing and validate the data | Data Integration Developer, Data Integration Architect
Perform UAT | Business Analyst/Data Stewards
Support UAT | Data Integration Developer, Data Integration Architect
Obtain Sign off from BU Lead | Technical Project Manager, Solution Architect, User Acceptance Test lead
Deploy
Set up PROD setup and Deployment | Informatica Administrator, Data Integration Developer
Deploy the code in Production | Informatica Administrator, Data Integration Developer, Data Integration Architect
Run Day 0/Initial load | Informatica Administrator, Data Integration Developer, Data Integration Architect
Operate
Transfer knowledge to Operations team | Data Integration Developer, Data Integration Architect, Solution Architect
Schedule the jobs to run in Production and enable the schedule | Informatica Administrator
Create project closure report | Business Project Manager, Technical Project Manager